## Project tasks
Project name | Launch website
Plan owner | Gareth Dwyer
Project start date | 2025-10-03 08:00
Project finish date | 2025-11-25 17:00
Duration | 11 days
% complete | 20%
Exported on | 2025-10-06 12:53
Task number | Outline number | Name | Assigned to | Start | Finish | Duration | Bucket | % complete | Priority | Depends on | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Sprint | Goal
1 | 1 | Design website |  | 2025-11-11 09:00 | 2025-11-13 17:00 | 3 days | Bucket 1 | 75% | Medium |  | 2FS |  |  |  | No | Use Figma |  |  |  | Backlog
2 | 2 | Build |  | 2025-11-14 09:00 | 2025-11-21 17:00 | 6 days |  | 0% | Medium | 1FS | 5FS |  |  |  | No
3 | 2.1 | Make web app |  | 2025-11-14 09:00 | 2025-11-18 17:00 | 3 days | Bucket 1 | 0% | Medium | [5 empty] | No |  |  |  |  | Backlog
4 | 2.2 | Make mobile app |  | 2025-11-19 09:00 | 2025-11-21 17:00 | 3 days | Bucket 1 | 0% | Medium | [5 empty] | No |  |  |  |  | Backlog
5 | 3 | Test |  | 2025-11-24 09:00 | 2025-11-25 17:00 | 2 days |  | 0% | Important | 2FS |  |  |  |  | No | Unit and integration tests
6 | 3.1 | Integration test |  | 2025-11-24 09:00 | 2025-11-25 17:00 | 2 days | Bucket 1 | 0% | Medium | [5 empty] | No |  |  |  |  | Backlog